PNA Communication and Engagement Plan 2024-2025

From 1st April 2013, statutory responsibility for publishing and updating a statement of the need for pharmaceutical services passed to health and wellbeing boards (HWBs). Pharmaceutical Needs Assessments (PNAs) are used when considering applications for new pharmacies in an area and by commissioners to identify local health needs that could be addressed by pharmacy services. HWBs have a duty to ensure revised PNAs are in place by October 2025. The coordination and production of the pan-Lancashire PNA covering the three upper tier local authorities has been delegated to a steering group of partners. This collaborative approach gives ownership of the PNA process across the three localities and aims to encourage the widest range of stakeholders and those with an interest in the PNA to participate in its development.

The purpose of this plan is to ensure the timely delivery of key messages and actions at appropriate stages of PNA development which will take the form of briefings, update reports, links to national campaigns and formal consultation over the course of the year so that HWBs and stakeholders have a clear understanding of the focus, process, and methodology of the PNA and have the opportunity to actively contribute to its development.

| Author: PNA working group |  |  |
| --- | --- | --- |
| Version | Date | Status |
| 1 | 28 Aug 2024 | First draft for comments from Steering Group |
|  | - | Approved for publishing |

Provisional dates shown in yellow

| Message/Action | Method | Stakeholders | Start date | End date | Frequency | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PNA Awareness Raising for HWBs to explain what it is, who produces it, why and how it’s used? | - Agenda item HWBs - Website article for HWB/JSNA sites (Check current website) | Health Practitioners, Pharmacies, HWB members, Patients and Public | Aug 2024 | HWB dates: B’pool Done BwD 5th Sept LCC 12th Nov | To be updated periodically | - PNA Working Group rep in each locality |  |
| Share project documents on JSNA website | T.O.R., risks and project plan completed | Health Practitioners, Pharmacies, HWB members, Patients and Public | Aug 2024 |  | To be updated periodically | PNA Working Group rep in each locality |  |
| To ascertain the services provided by community pharmacies | - Electronic Questionnaire via PharmOutcomes - Article in Community Pharmacy Lancashire and South Cumbria weekly bulletin | Community Pharmacies – 4 weeks to respond | Send 3rd Jan 2025 Early Jan 2025 | 31st Jan | Once | PNA Steering Group Mubasher Ali |  |
| Public consultation on pharmaceutical services provision | Electronic Questionnaire | Conducted by Healthwatchs | TBC |  | Once | PNA Steering Group |  |
| Comments of steering group on first iteration of PNA | Draft PNA | HWBs, ICB (pharmacy), CPLSC, ICB/PBP, LPN, Public Health, Local Healthwatch | 1st June 2025 | 15th June 2025 | Once | PNA Steering Group |  |
| PNA awareness raising – to coincide with the 60 day consultation | Email, social media, CPLSC bulletin, engage Healthwatch and CVS | HWB, ICB (pharmacy), CPLSC, ICB/PBP, LPN, Public Health, CSU, Dispensing Doctors, Providers, Local Healthwatch, Patients and Public | 1st July 2025 | 1st Sept 2025 | Once | PNA Steering Group |  |
| Feedback on outcome of 60 day consultation | Summary report and email to link to HWB/JSNA websites where it will be uploaded | HWB, ICB (pharmacy), CPLSC, ICB/PBP, LPN, Public Health, CSU, Dispensing Doctors, Providers, Local Healthwatch, Patients and Public | 1st Sept 2025 | 1st Oct 2025 | Once | PNA Steering Group |  |
| Final version of PNA to be approved by each HWB | PNA, Report | HWBs | 20th Sept 2025 |  | Once | PNA Steering Group |  |
| Disseminate final version of PNA | PNA and email link to HWB/JSNA websites where it will be uploaded | HWB, CPLSC, LPN, ICB/PBP, CSU, Local Healthwatch, Patients, Service users, Local Healthwatch, Public Health, Providers | 1st Oct 2025 |  | Once | PNA Steering Group |  |
| Notification of amendments to PNA | Email link to PNA and amendments | HWB, CPLSC, LPN, ICB/PBP, CSU, Local Healthwatch, Patients, Service users, Local Healthwatch, Public Health, Providers | As req’d |  | As req’d | PNA Steering Group |  |